## Dashboard
SLA ref | SLA desc | Expected | Min | Complaince
EEM 2.1 | IIA (Initial Impact Assessments) requests are delivered to DOM within 9 working days of the initial request being accepted. | 90% | 85% | 100%
EEM 2.2 | Delivery Packages are delivered on time. | 90% | 85% | 100%
EEM 2.3 | Deliveries to Non Amdocs Test Phase are delivered on time. | 90% | 85% | 0%
EEM 2.4 | Deliveries to Production are delivered on time. | 90% | 85% | NA
EEM 2.5 | Critical/High priority incidents (P1 and P2) raised after a release goes live into production. | 2 | 3 | 0
EEM 2.6 | CCR scheduling requests are delivered within 2 working days of initial request. | 96% | 95% | 87%
EEM 2.7 | PCR IIAs (Initial Impact Assessments) are delivered within 2 working days of initial request. | 87% | 84% | 75%
EEM 2.8 | High Level Configuration Designs (HLCD) are delivered on Time. | 90% | 85% | 87%
EEM 3.1 | Rejected IIAs with root cause Amdocs are re-delivered within 3 working days. | 0 | 1 | NA
EEM 3.2 | Estimate Accuracy. | +/-30% | +/-30% | -33.333336%
EEM 3.3 | Detailed Configuration Designs Delivered on Time. (DCD) | 90% | 87% | 87%
EEM 3.4 | CCRs ready to be delivered to production on time | 99% | 97% | 87%
EEM 3.5 | PCRs delivered to Test on time. | 90% | 85% | 87%
EEM 3.6 | PCRs delivered to Production on time. | 90% | 85% | 87%
EEM 3.7 | Quantity of defects detected at testing (defect density) | Baseline | Baseline | NA
EEM 3.8 | Severity 1 showstopper defects found in test are fixed or answered within 2 days. | 0 | 2 | NA
EEM 3.9 | Severity 1 showstopper defects found in test fixed 1st time | 0 | 2 | NA
EEM 3.10 | Planned Change success rate | 1 | 4 | 0
EEM 3.11 | Medium (P3/P4) Incident raised after a release goes live into production | 6 (Baseline) | 8 (Baseline) | 0
EEM 3.12 | Low priority (P5/P6) Incident raised after a release goes live into production | 8 (Baseline) | 12 (Baseline) | 0
EEM 3.13 | High priority (P1/P2) problem solutions ready for delivery to a third party within target working days. | 1 | 2 | 0
EEM 3.14 | Problem Root Causes found for High Priority (P1/P2 ) Problem Records within target working days. | 1 | 2 | 1
EEM 3.15 | Deployed Problem Records successfully fix the root cause | 1 | 2 | 0
EEM 4.1 | Stakeholder Satisfaction - Release Survey | 80% | 60%
EEM 4.2 | IIA Request estimates (M0 for Unity) have a confirmed request approval or rejection to DOM within 1 working day of request receipt. | 96% | 94% | NA
EEM 4.3 | All IIA (Initial Impact Assessments) requests are delivered to DOM within 15 working days of the initial request being accepted. | 100% | 95% | 60%
EEM 4.4 | Work Requests (WR) have a confirmed acknowledgement to DOM within 1 working day of request receipt. | 90% | 85% | 72%
EEM 4.5 | WR cost is to be provided 5 days after DOM have made the request in QC. | 85% | 82% | 85%
EEM 4.6 | Severity 2 critical defects are fixed or answered within 3 days. | 1 | 4 | 1
EEM 4.7 | Severity 2 critical defects found in test fixed 1st time | 1 | 3 | 0
EEM 4.8 | Concession defects are implemented by the agreed date. | 100% | 95% | NA
EEM 4.9 | HLCD quality is to have no more than an expected combined average of the agreed Points (issues) per HLCD during a month. | 4 | 5 | 24
EEM 4.10 | Medium priority (P3) problem solutions ready for delivery to a third party within target working days. | 1 | 2 | 0
EEM 4.11 | Low priority (P4) problem solutions ready for delivery to a third party within target working days. | 1 | 2 | 0
EEM 4.12 | Problem Root Causes found for Medium Priority (P3 ) Problem Records within target working days. | 1 | 2 | 0
EEM 4.13 | Problem Root Causes found for Low Priority (P4 ) Problem Records within target working days. | 1 | 2 | 0
ELF 4.1 NEW | Quantity of defects found in test following ELF Config delivery. PC (NonAmdocs) | Baseline | Baseline | NA

## IIA & HLD Request Tracker
ELD ID | Project Name | Service Type | Acknowledment Date for HLD & IIA | SOW submission Date for HLD/WIF submission of IIA | Expected Delivery date to meet 7 day IIA SLA | Delivery Date(IIA & HLD) planned | Delivery Date actual | IIA delivered within 7 days? | HLD delivery dates provided within 5 days? | HLD delivered as per agreed timeline? | IIA agreed Date | Actual IIA re-delivered date | IIA re-delivered as per agreed timeline | Requestor | Comments
etyy | edryy | HLD | TBD | 2017-11-22 01:08:00 | NA | 2016-02-01 20:29:00 |  | NA | Yes | On Hold | NA | NA | NA | wrer
fjkko | dghhj | HLD | TBD | 2019-01-20 06:59:00 | NA | 2019-01-23 00:00:00 | 2019-01-23 00:00:00 | NA | Yes | Yes | NA | NA | NA | hj;l;
22222 | test7 | IIA | NA | TBD | 2019-01-11 04:40:00 | TBD |  | On Hold | NA | NA |  |  | NA | Amdocs
98076 | uiop | IIA | NA | TBD | 2019-01-02 04:40:00 | TBD |  | On Hold | NA | NA |  |  | NA | Amdocs
new | asdd | IIA | NA | 2019-01-16 01:59:00 | 2019-01-24 08:30:00 | TBD |  | No | NA | NA |  |  | NA | asd
8907 | test5 | IIA | NA | 2018-12-24 10:11:00 | 2019-01-08 10:12:00 | 2019-01-08 10:10:00 | 2019-01-08 10:10:00 | Yes | NA | NA |  |  | NA | Amdocs
00000 | test6 | IIA | NA | 2019-01-18 10:10:00 | 2019-01-28 10:10:00 | TBD |  | No | NA | NA |  |  | NA | Amdocs